## Summary
Item | Value
Project | Sample: Waller garden apartments
Site option | Option A
Scenario | Base case
Inputs hash | 332a5c7a
Scope | Feasibility / schematic level only. The plan set is a schematic-design set for planning and pricing conversations. It is not a permit set and not construction documents, and it has not been prepared, sealed or reviewed by a licensed architect or engineer. Parcel lines come from appraisal-district or provider data, not a boundary survey. Costs are parametric estimates from a single-project workbook and house rates, not contractor bids. Market rents, cap rates and financing terms are assumptions, not appraisals. Use the outputs to decide whether to pursue a site, not to build from.
Site acres | 15.9742
Gross building sf | 425610.9
Units | 389
Parking spaces | 657
Land and closing | 2639000
Construction contract | 58846996.3551
Soft costs | 7576402.51
Developer fee | 2135950.4804
Project cost before financing | 71198349.3455
Construction interest | 7602108.1935
Loan fees | 427190.0961
Total development cost | 79227647.635
Stabilized NOI | 3853211.0225
Yield on cost | 4.863%
Unlevered IRR | 5.333%
Levered IRR | 3.505%
Unlevered NPV | -16007493.8627
Levered NPV | -11255356.2216
Equity multiple | 1.2837
Peak equity | 37353300.0814
Levered profit | 10596475.8575
DSCR | 1.25
Margin (for sale)

## Assumptions
Group | Key | Assumption | Value | Unit | Default | Usual low | Usual high | Source kind | Source | As of | Confidence | Market check
cost | landPrice | Land price | 2600000 | usd |  |  |  | user | Asking / contract price entered at intake |  | medium
cost | landClosingPct | Land closing costs | 1.5 | pct |  | 0.5 | 3 | house | Title, survey, legal at closing (1–2%) |  | low
cost | locationFactor | Location cost factor | 1 | x |  | 0.8 | 1.3 | house | 1.00: the site is in the region the cost library and parametric rates were priced for (Waller / Houston area) |  | medium-low
cost | materialsShare | Materials share of hard cost (escalated by the PPI) | 0.55 | share |  | 0.4 | 0.65 | house | Typical materials share of building cost (labor and fees are the rest) |  | low
cost | escalationPct | Forward cost escalation | 3.5 | pct |  | 0 | 8 | house | Annual construction-cost escalation to the construction midpoint |  | low
cost | gcFeePct | GC fee on library lines | 12 | pct |  | 6 | 18 | library | Finishes Solutions budget template: company profit 12% of hard cost | 2026-08-10 | medium-low
cost | devFeePct | Developer fee (of total project cost) | 3 | pct |  | 1.5 | 5 | house | Developer fee, a share of total project cost before financing (2–5%) |  | low
cost | contPct | Contingency | 5 | pct |  | 3 | 10 | house | Hard-cost contingency at concept stage (3–10%) |  | low
cost | sitePrepPsf | Site prep | 3 | psf |  | 1.5 | 5 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
cost | pavingPsf | Paving | 7.5 | psf |  | 5.5 | 10 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
cost | stallCost | Parking a space | 2750 | usd |  | 1800 | 4500 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
cost | pondPerAcFt | Detention pond | 30000 | usd |  | 15000 | 60000 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
revenue | rents.Studio | Studio rent | 1175 | mo |  | 900 | 1500 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low | ZIP 77484 typical rent $1,614/mo (2026-09, all homes; +1.8% a year): Zillow Observed Rent Index (ZORI), all homes, smoothed (data/area.json rents)
revenue | rents.1 BR | 1 BR rent | 1425 | mo |  | 1050 | 1800 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low | ZIP 77484 typical rent $1,614/mo (2026-09, all homes; +1.8% a year): Zillow Observed Rent Index (ZORI), all homes, smoothed (data/area.json rents)
revenue | rents.2 BR | 2 BR rent | 1795 | mo |  | 1350 | 2300 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low | ZIP 77484 typical rent $1,614/mo (2026-09, all homes; +1.8% a year): Zillow Observed Rent Index (ZORI), all homes, smoothed (data/area.json rents)
revenue | rents.3 BR | 3 BR rent | 2150 | mo |  | 1650 | 2800 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low | ZIP 77484 typical rent $1,614/mo (2026-09, all homes; +1.8% a year): Zillow Observed Rent Index (ZORI), all homes, smoothed (data/area.json rents)
revenue | otherPerUnit | Other income a unit | 75 | mo |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
revenue | vacancyPct | Vacancy | 7 | pct |  | 3 | 15 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
revenue | creditPct | Credit loss | 1 | pct |  | 0 | 3 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
operations | opexPerUnit | Apartment operating costs | 4600 | usd |  | 3800 | 6500 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
operations | taxPct | Property tax rate | 2.5 | pct |  | 1.8 | 3.2 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
operations | taxBasisPct | Taxable share of cost | 70 | pct |  | 55 | 100 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
operations | mgmtPct | Management fee | 3 | pct |  | 2 | 8 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
financing | rate | Construction rate | 6.9 | pct |  | 5.5 | 10 | derived | SOFR 3.90% (FRED, 2026-10-22) + 3.00% construction-loan spread (house) | 2026-10-22 | medium
financing | permRate | Permanent rate | 6.71 | pct |  | 4.5 | 8 | derived | 10-yr Treasury 4.96% (FRED, 2026-10-22) + 1.75% permanent-loan spread (house) | 2026-10-22 | medium
financing | ltc | Loan to cost | 60 | pct |  | 45 | 75 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
financing | loanFeePct | Loan fee | 1 | pct |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
financing | amort | Amortization | 30 | years |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
financing | ltv | Loan to value | 65 | pct |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
financing | dscr | Debt coverage (DSCR) | 1.25 | x |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
returns | marketCap | Market cap rate | 5.5 | pct |  | 4.5 | 9 | house | Going-in cap rate by use, Houston suburban 2026 (UNVERIFIED: the platform has no sale comps) |  | low
returns | exitCap | Exit cap rate | 5.75 | pct |  | 4.5 | 9.5 | house | Exit cap = market cap + 0.25% |  | low
returns | dispPct | Sale costs | 2 | pct |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
returns | rentGrowth | Rent growth | 3 | pct |  | 0 | 5 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
returns | expGrowth | Expense growth | 3 | pct |  | 1 | 5 | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
returns | hold | Hold after stabilizing | 5 | years |  |  |  | house | Platform default: 2026 Houston / Katy / Waller suburban market assumption (UNVERIFIED) | 2026 | low
returns | discountRate | Discount rate (NPV) | 10 | pct |  | 6 | 18 | house | Discount rate for net present value: a levered development hurdle |  | low
schedule | sched.pre | Pre-development | 9 | months |  |  |  | house | Schedule from the program’s size and type (lib/proforma.mjs scheduleFor) |  | low
schedule | sched.build | Construction | 25 | months |  |  |  | house | Schedule from the program’s size and type (lib/proforma.mjs scheduleFor) |  | low
schedule | sched.lease | Lease-up | 19 | months |  |  |  | house | Schedule from the program’s size and type (lib/proforma.mjs scheduleFor) |  | low

## Budget
Group | CSI | Division | Item | Qty | Unit | Rate | Amount | Edited | Off | Source | Confidence
hard | 01 01 00 | Division 01 — General Requirements | Project Management | 420210.9 | residential sf | 8.0097 | 3365768.22 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 02 00 | Division 01 — General Requirements | Insurance | 420210.9 | residential sf | 1.6233 | 682129.03 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 04 00 | Division 01 — General Requirements | Equipment & Supplies | 420210.9 | residential sf | 0.74757 | 314138.37 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 05 00 | Division 01 — General Requirements | Security | 420210.9 | residential sf | 0.19223 | 80778.44 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 50 00 | Division 01 — General Requirements | Temporary Facilities (Toilets, Fencing, Power, Water) | 420210.9 | residential sf | 1.2816 | 538522.91 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 70 00 | Division 01 — General Requirements | Execution & Closeout | 420210.9 | residential sf | 0.58738 | 246823 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 74 00 | Division 01 — General Requirements | Construction Waste Management & Disposal | 420210.9 | residential sf | 2.3282 | 978316.63 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 06 00 | Division 01 — General Requirements | Testing & Surveying | 420210.9 | residential sf | 0.42718 | 179507.64 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 01 07 00 | Division 01 — General Requirements | Inspections | 420210.9 | residential sf | 0.69418 | 291699.91 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 03 30 00 | Division 03 — Concrete | Foundation / Slab w/ Termite Treatment | 420210.9 | residential sf | 5.6068 | 2356037.75 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 04 40 00 | Division 04 — Masonry | Stone Assemblies | 420210.9 | residential sf | 0.88641 | 372478.35 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 05 10 00 | Division 05 — Metals | Structural Metal / Stairs / Handrails / Dumpster Doors | 420210.9 | residential sf | 1.6553 | 695592.1 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 06 10 00 | Division 06 — Wood, Plastics, and Composites | Rough Carpentry / Framing / Roof Framing / Sheathing / Siding | 420210.9 | residential sf | 21.9466 | 9222204.92 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 07 21 00 | Division 07 — Thermal and Moisture Protection | Insulation | 420210.9 | residential sf | 1.4845 | 623789.04 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 07 40 00 | Division 07 — Thermal and Moisture Protection | Roofing | 420210.9 | residential sf | 1.367 | 574424.44 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 07 60 00 | Division 07 — Thermal and Moisture Protection | Gutters / Downspouts | 420210.9 | residential sf | 0.35243 | 148093.8 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 10 00 | Division 08 — Openings | Doors & Frames (Exterior) | 420210.9 | residential sf | 2.6699 | 1121922.74 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 50 00 | Division 08 — Openings | Windows | 420210.9 | residential sf | 1.2922 | 543010.61 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 70 00 | Division 08 — Openings | Door Hardware (Exterior) | 420210.9 | residential sf | 0.1068 | 44876.91 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 90 00 | Division 09 — Finishes | Exterior Painting & Coating | 420210.9 | residential sf | 0.50194 | 210921.47 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 21 10 00 | Division 21 — Fire Suppression | Water-Based Fire Suppression | 420210.9 | residential sf | 1.4951 | 628276.73 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 22 05 00 | Division 22 — Plumbing | Plumbing | 420210.9 | residential sf | 8.6718 | 3644005.06 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 23 05 00 | Division 23 — Heating, Ventilating, and Air Conditioning (HVAC) | HVAC | 420210.9 | residential sf | 6.2049 | 2607348.45 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 26 05 00 | Division 26 — Electrical | Electrical | 420210.9 | residential sf | 6.9311 | 2912511.43 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 27 10 00 | Division 27 — Communications | Structured Cabling (Ethernet & Cameras) | 420210.9 | residential sf | 0.86505 | 363502.97 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 28 46 00 | Division 28 — Electronic Safety and Security | Fire Detection & Alarm | 420210.9 | residential sf | 1.4524 | 610325.97 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 06 20 00 | Division 06 — Wood, Plastics, and Composites | Finish Carpentry / Baseboards / Casing / Trim | 420210.9 | residential sf | 2.2748 | 955878.17 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 11 00 | Division 08 — Openings | Interior Doors & Frames | 420210.9 | residential sf | 1.399 | 587887.52 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 71 00 | Division 08 — Openings | Interior Door Hardware | 420210.9 | residential sf | 0.21359 | 89753.82 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 83 00 | Division 08 — Openings | Mirrors | 420210.9 | residential sf | 0.30971 | 130143.04 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 20 00 | Division 09 — Finishes | Plaster & Gypsum Board | 420210.9 | residential sf | 5.0408 | 2118190.13 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 30 00 | Division 09 — Finishes | Tiling / Bathroom & Backsplash | 420210.9 | residential sf | 1.0252 | 430818.33 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 60 00 | Division 09 — Finishes | Flooring | 420210.9 | residential sf | 1.9117 | 803296.68 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 91 00 | Division 09 — Finishes | Interior Painting & Coating | 420210.9 | residential sf | 2.3282 | 978316.63 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 14 00 | Division 10 — Specialties | Signage / Unit & Building Numbers | 420210.9 | residential sf | 0.1068 | 44876.91 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 28 00 | Division 10 — Specialties | Toilet, Bath & Laundry Accessories | 420210.9 | residential sf | 0.66214 | 278236.84 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 11 31 00 | Division 11 — Equipment | Residential Appliances | 420210.9 | residential sf | 3.7165 | 1561716.45 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 21 00 | Division 12 — Furnishings | Window Blinds | 420210.9 | residential sf | 0.35243 | 148093.8 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 30 00 | Division 12 — Furnishings | Casework / Stock Cabinets | 420210.9 | residential sf | 2.1466 | 902025.88 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 36 00 | Division 12 — Furnishings | Countertops | 420210.9 | residential sf | 1.2068 | 507109.08 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 55 00 | Division 10 — Specialties | Mailboxes | 420210.9 | residential sf | 0.26699 | 112192.27 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 28 10 00 | Division 28 — Electronic Safety and Security | Electronic Access Control & Intrusion Detection | 420210.9 | residential sf | 1.2175 | 511596.77 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 32 31 00 | Division 32 — Exterior Improvements | Fences & Gates / Motors | 420210.9 | residential sf | 1.3884 | 583399.82 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 32 33 00 | Division 32 — Exterior Improvements | Site Furnishings / Benches / Bike Racks | 420210.9 | residential sf | 0.4699 | 197458.4 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 10 00 | Division 08 — Openings | Doors & Frames (amenity) | 5400 | amenity sf | 2.6699 | 14417.48 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 40 00 | Division 08 — Openings | Storefront / Glass Partitions (amenity) | 5400 | amenity sf | 22.5981 | 122029.56 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 22 30 00 | Division 22 — Plumbing | Plumbing Fixtures (amenity) | 5400 | amenity sf | 4.432 | 23933.02 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 26 50 00 | Division 26 — Electrical | Light Fixtures (amenity) | 5400 | amenity sf | 4.4 | 23760.01 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 27 10 00 | Division 27 — Communications | Structured Cabling (Ethernet & Cameras) (amenity) | 5400 | amenity sf | 10.0816 | 54440.41 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 27 11 00 | Division 27 — Communications | Communications Equipment Room (amenity) | 5400 | amenity sf | 7.2942 | 39388.56 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 28 10 00 | Division 28 — Electronic Safety and Security | Access Control / Intrusion Detection (amenity) | 5400 | amenity sf | 12.634 | 68223.52 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 28 20 00 | Division 28 — Electronic Safety and Security | Electronic Surveillance / Cameras (amenity) | 5400 | amenity sf | 4.2718 | 23067.97 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 28 46 00 | Division 28 — Electronic Safety and Security | Fire Detection & Alarm (amenity) | 5400 | amenity sf | 5.3398 | 28834.96 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 06 20 00 | Division 06 — Wood, Plastics, and Composites | Finish Carpentry / Millwork / Trim (amenity) | 5400 | amenity sf | 8.5117 | 45962.93 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 11 00 | Division 08 — Openings | Interior Doors & Frames (amenity) | 5400 | amenity sf | 4.6563 | 25144.09 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 08 71 00 | Division 08 — Openings | Door Hardware (amenity) | 5400 | amenity sf | 3.1932 | 17243.31 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 30 00 | Division 09 — Finishes | Tiling / Bathroom & Backsplash (amenity) | 5400 | amenity sf | 8.768 | 47347.01 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 09 60 00 | Division 09 — Finishes | Flooring (amenity) | 5400 | amenity sf | 5.0942 | 27508.55 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 14 00 | Division 10 — Specialties | Signage (amenity) | 5400 | amenity sf | 0.17087 | 922.72 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 28 00 | Division 10 — Specialties | Toilet, Bath & Laundry Accessories (amenity) | 5400 | amenity sf | 8.4796 | 45789.92 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 10 44 00 | Division 10 — Specialties | Fire Protection Specialties / Extinguishers (amenity) | 5400 | amenity sf | 0.13884 | 749.71 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 11 60 00 | Division 11 — Equipment | Entertainment Equipment / Game & Media Room (amenity) | 5400 | amenity sf | 3.2039 | 17300.98 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 11 65 00 | Division 11 — Equipment | Athletic & Recreational / Fitness Equipment (amenity) | 5400 | amenity sf | 5.3398 | 28834.96 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 30 00 | Division 12 — Furnishings | Casework / Stock Cabinets (amenity) | 5400 | amenity sf | 5.6922 | 30738.07 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 36 00 | Division 12 — Furnishings | Countertops (amenity) | 5400 | amenity sf | 4.2718 | 23067.97 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 50 00 | Division 12 — Furnishings | Leasing Office / Clubhouse Furniture (amenity) | 5400 | amenity sf | 1.8583 | 10034.57 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
hard | 12 60 00 | Division 12 — Furnishings | Multiple / Amenity Seating (amenity) | 5400 | amenity sf | 1.0039 | 5420.97 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-01 | Custom | Architect | 420210.9 | residential sf | 2.65 | 1113558.88 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-02 | Custom | Civil Engineer | 420210.9 | residential sf | 1.58 | 663933.22 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-03 | Custom | Structural Engineer | 420210.9 | residential sf | 1.17 | 491646.75 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-04 | Custom | MEP Engineer | 420210.9 | residential sf | 0.33 | 138669.6 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-05 | Custom | Landscape Architect | 420210.9 | residential sf | 0.15 | 63031.63 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-06 | Custom | Geotechnical Engineer | 420210.9 | residential sf | 0.18 | 75637.96 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-07 | Custom | Environmental Study | 420210.9 | residential sf | 0.04 | 16808.44 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-08 | Custom | TxDOT Driveway Permitting | 420210.9 | residential sf | 0.28 | 117659.05 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-09 | Custom | Traffic Impact Analysis | 420210.9 | residential sf | 0.36 | 151275.92 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-10 | Custom | Flood Plain Mitigation | 420210.9 | residential sf | 0.18 | 75637.96 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-11 | Custom | Pad Elevation Certificates | 420210.9 | residential sf | 0.22 | 92446.4 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-12 | Custom | A/E Construction Administration | 420210.9 | residential sf | 0.39 | 163882.25 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-13 | Custom | Surveyor | 420210.9 | residential sf | 0.13 | 54627.42 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-14 | Custom | Renderings | 420210.9 | residential sf | 0.1 | 42021.09 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-15 | Custom | Reimbursables | 420210.9 | residential sf | 0.18 | 75637.96 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-16 | Custom | Plan Printing | 420210.9 | residential sf | 0.06 | 25212.65 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-17 | Custom | Precon Services (6 mo) | 420210.9 | residential sf | 0.29 | 121861.16 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-18 | Custom | Design Contingency (≈10%) | 420210.9 | residential sf | 0.83 | 348775.05 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-20 | Custom | Water & Sewer Impact & Tap Fees | 420210.9 | residential sf | 7.5 | 3151581.75 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-21 | Custom | Permitting & Inspection Fees | 420210.9 | residential sf | 0.45 | 189094.91 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-22 | Custom | Plan Review Fees | 420210.9 | residential sf | 0.15 | 63031.63 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
soft | SC-23 | Custom | Fees Contingency (≈10%) | 420210.9 | residential sf | 0.81 | 340370.83 | FALSE | FALSE | Finishes Solutions budget workbook (Budget For Projects 3.0), Waller County TX multifamily, back-solved $/SF | medium-low
site | 31 00 00 | Division 31 — Earthwork | Site preparation: clearing, mass grading, lime-stabilized pads, erosion control, on-site utilities, landscaping, lighting | 674621.6375 | sf developed | 3.1907 | 2152532.16 | FALSE | FALSE | Platform parametric rate, 2026 Houston / Katy / Waller suburban starting point (UNVERIFIED; range in the pro forma notes); quantity from the concept layout | low
site | 32 12 00 | Division 32 — Exterior Improvements | Drives, fire lanes and plazas outside the parking lots (concrete; truck courts at 1.25×) | 158041.554 | sf | 7.9768 | 1260667.86 | FALSE | FALSE | Platform parametric rate, 2026 Houston / Katy / Waller suburban starting point (UNVERIFIED; range in the pro forma notes); quantity from the concept layout | low
site | 32 17 00 | Division 32 — Exterior Improvements | Surface parking spaces: paving, striping, lighting, islands | 657 | spaces | 2924.8313 | 1921614.16 | FALSE | FALSE | Platform parametric rate, 2026 Houston / Katy / Waller suburban starting point (UNVERIFIED; range in the pro forma notes); quantity from the concept layout | low
site | 33 46 00 | Division 33 — Utilities | Detention pond: excavation, outfall structure, slopes and seeding | 8.7858 | ac-ft | 31907.2505 | 280331.13 | FALSE | FALSE | Platform parametric rate, 2026 Houston / Katy / Waller suburban starting point (UNVERIFIED; range in the pro forma notes); quantity from the concept layout | low
site | 11 68 00 | Division 11 — Equipment | Amenity pieces on the plan: courts, pool and deck, playground | 1 | ls | 262064.8838 | 262064.88 | FALSE | FALSE | Platform parametric rate, 2026 Houston / Katy / Waller suburban starting point (UNVERIFIED; range in the pro forma notes); quantity from the concept layout | low
|  |  | GC fee (library lines) |  |  |  | 5402659.0416
|  |  | Contingency |  |  |  | 2544968.4435
|  |  | Developer fee |  |  |  | 2135950.4804
|  |  | Land and closing |  |  |  | 2639000
|  |  | Construction interest (pro forma) |  |  |  | 7602108.1935
|  |  | Loan fees (pro forma) |  |  |  | 427190.0961
|  |  | TOTAL DEVELOPMENT COST |  |  |  | 79227647.635

## CSI
Division | Amount | Share of contract
Division 01 — General Requirements | 6677684.15 | 11.35%
Division 03 — Concrete | 2356037.75 | 4.004%
Division 04 — Masonry | 372478.35 | 0.633%
Division 05 — Metals | 695592.1 | 1.182%
Division 06 — Wood, Plastics, and Composites | 10224046.02 | 17.37%
Division 07 — Thermal and Moisture Protection | 1346307.28 | 2.288%
Division 08 — Openings | 2696429.08 | 4.582%
Division 09 — Finishes | 4616398.8 | 7.845%
Division 10 — Specialties | 482768.37 | 0.8204%
Division 11 — Equipment | 1869917.27 | 3.178%
Division 12 — Furnishings | 1626490.34 | 2.764%
Division 21 — Fire Suppression | 628276.73 | 1.068%
Division 22 — Plumbing | 3667938.08 | 6.233%
Division 23 — Heating, Ventilating, and Air Conditioning (HVAC) | 2607348.45 | 4.431%
Division 26 — Electrical | 2936271.44 | 4.99%
Division 27 — Communications | 457331.94 | 0.7772%
Division 28 — Electronic Safety and Security | 1242049.19 | 2.111%
Division 31 — Earthwork | 2152532.16 | 3.658%
Division 32 — Exterior Improvements | 3963140.24 | 6.735%
Division 33 — Utilities | 280331.13 | 0.4764%
Profit — GC fee on library lines (12%) | 5402659.0416 | 9.181%
Construction contingency | 2544968.4435 | 4.325%
Contract sum | 58846996.3551 | 100%

## Monthly
Month | Cost | NOI | Unlevered | Levered
0 | 2639000 | 0 | -2639000 | -2639000
1 | 294637.8754 | 0 | -294637.8754 | -294637.8754
2 | 294637.8754 | 0 | -294637.8754 | -294637.8754
3 | 294637.8754 | 0 | -294637.8754 | -294637.8754
4 | 294637.8754 | 0 | -294637.8754 | -294637.8754
5 | 294637.8754 | 0 | -294637.8754 | -294637.8754
6 | 294637.8754 | 0 | -294637.8754 | -294637.8754
7 | 294637.8754 | 0 | -294637.8754 | -294637.8754
8 | 294637.8754 | 0 | -294637.8754 | -294637.8754
9 | 1362613.1156 | 0 | -1362613.1156 | -1362613.1156
10 | 215547.511 | 0 | -215547.511 | -215547.511
11 | 362284.1804 | 0 | -362284.1804 | -362284.1804
12 | 646537.5147 | 0 | -646537.5147 | -646537.5147
13 | 1050446.8314 | 0 | -1050446.8314 | -1050446.8314
14 | 1548633.0227 | 0 | -1548633.0227 | -1548633.0227
15 | 2109793.218 | 0 | -2109793.218 | -2109793.218
16 | 2698667.6584 | 0 | -2698667.6584 | -2698667.6584
17 | 3278255.1971 | 0 | -3278255.1971 | -3278255.1971
18 | 3812138.2175 | 0 | -3812138.2175 | -3812138.2175
19 | 4266770.8859 | 0 | -4266770.8859 | -4266770.8859
20 | 4613586.9597 | 0 | -4613586.9597 | -2131549.3823
21 | 4830794.7096 | 0 | -4830794.7096 | 0
22 | 4904746.1737 | 0 | -4904746.1737 | 0
23 | 4830794.7096 | 0 | -4830794.7096 | 0
24 | 4613586.9597 | 0 | -4613586.9597 | 0
25 | 4266770.8859 | 0 | -4266770.8859 | 0
26 | 3812138.2175 | 0 | -3812138.2175 | 0
27 | 3278255.1971 | 0 | -3278255.1971 | 0
28 | 2698667.6584 | 0 | -2698667.6584 | 0
29 | 2109793.218 | 0 | -2109793.218 | 0
30 | 1548633.0227 | 0 | -1548633.0227 | 0
31 | 1050446.8314 | 0 | -1050446.8314 | 0
32 | 646537.5147 | 0 | -646537.5147 | 0
33 | 362284.1804 | 0 | -362284.1804 | 0
34 | 1283522.7512 | 0 | -1283522.7512 | 0
35 | 0 | -230412.1448 | -230412.1448 | 0
36 | 0 | -199772.5302 | -199772.5302 | 0
37 | 0 | -169132.9156 | -169132.9156 | 0
38 | 0 | -138493.3009 | -138493.3009 | 0
39 | 0 | -107853.6863 | -107853.6863 | 0
40 | 0 | -77214.0717 | -77214.0717 | 0
41 | 0 | -46574.457 | -46574.457 | 0
42 | 0 | -15934.8424 | -15934.8424 | 0
43 | 0 | 14704.7722 | 14704.7722 | 0
44 | 0 | 45344.3869 | 45344.3869 | 0
45 | 0 | 75984.0015 | 75984.0015 | 0
46 | 0 | 109822.3246 | 109822.3246 | 0
47 | 0 | 141381.1277 | 141381.1277 | 0
48 | 0 | 172939.9307 | 172939.9307 | 0
49 | 0 | 204498.7338 | 204498.7338 | 0
50 | 0 | 236057.5369 | 236057.5369 | 0
51 | 0 | 267616.34 | 267616.34 | 0
52 | 0 | 299175.143 | 299175.143 | 0
53 | 0 | 330733.9461 | 330733.9461 | -8873960.3432
54 | 0 | 330733.9461 | 330733.9461 | 66146.7892
55 | 0 | 330733.9461 | 330733.9461 | 66146.7892
56 | 0 | 330733.9461 | 330733.9461 | 66146.7892
57 | 0 | 330733.9461 | 330733.9461 | 66146.7892
58 | 0 | 340655.9645 | 340655.9645 | 76068.8076
59 | 0 | 340655.9645 | 340655.9645 | 76068.8076
60 | 0 | 340655.9645 | 340655.9645 | 76068.8076
61 | 0 | 340655.9645 | 340655.9645 | 76068.8076
62 | 0 | 340655.9645 | 340655.9645 | 76068.8076
63 | 0 | 340655.9645 | 340655.9645 | 76068.8076
64 | 0 | 340655.9645 | 340655.9645 | 76068.8076
65 | 0 | 340655.9645 | 340655.9645 | 76068.8076
66 | 0 | 340655.9645 | 340655.9645 | 76068.8076
67 | 0 | 340655.9645 | 340655.9645 | 76068.8076
68 | 0 | 340655.9645 | 340655.9645 | 76068.8076
69 | 0 | 340655.9645 | 340655.9645 | 76068.8076
70 | 0 | 350875.6434 | 350875.6434 | 86288.4865
71 | 0 | 350875.6434 | 350875.6434 | 86288.4865
72 | 0 | 350875.6434 | 350875.6434 | 86288.4865
73 | 0 | 350875.6434 | 350875.6434 | 86288.4865
74 | 0 | 350875.6434 | 350875.6434 | 86288.4865
75 | 0 | 350875.6434 | 350875.6434 | 86288.4865
76 | 0 | 350875.6434 | 350875.6434 | 86288.4865
77 | 0 | 350875.6434 | 350875.6434 | 86288.4865
78 | 0 | 350875.6434 | 350875.6434 | 86288.4865
79 | 0 | 350875.6434 | 350875.6434 | 86288.4865
80 | 0 | 350875.6434 | 350875.6434 | 86288.4865
81 | 0 | 350875.6434 | 350875.6434 | 86288.4865
82 | 0 | 361401.9127 | 361401.9127 | 96814.7558
83 | 0 | 361401.9127 | 361401.9127 | 96814.7558
84 | 0 | 361401.9127 | 361401.9127 | 96814.7558
85 | 0 | 361401.9127 | 361401.9127 | 96814.7558
86 | 0 | 361401.9127 | 361401.9127 | 96814.7558
87 | 0 | 361401.9127 | 361401.9127 | 96814.7558
88 | 0 | 361401.9127 | 361401.9127 | 96814.7558
89 | 0 | 361401.9127 | 361401.9127 | 96814.7558
90 | 0 | 361401.9127 | 361401.9127 | 96814.7558
91 | 0 | 361401.9127 | 361401.9127 | 96814.7558
92 | 0 | 361401.9127 | 361401.9127 | 96814.7558
93 | 0 | 361401.9127 | 361401.9127 | 96814.7558
94 | 0 | 372243.9701 | 372243.9701 | 107656.8132
95 | 0 | 372243.9701 | 372243.9701 | 107656.8132
96 | 0 | 372243.9701 | 372243.9701 | 107656.8132
97 | 0 | 372243.9701 | 372243.9701 | 107656.8132
98 | 0 | 372243.9701 | 372243.9701 | 107656.8132
99 | 0 | 372243.9701 | 372243.9701 | 107656.8132
100 | 0 | 372243.9701 | 372243.9701 | 107656.8132
101 | 0 | 372243.9701 | 372243.9701 | 107656.8132
102 | 0 | 372243.9701 | 372243.9701 | 107656.8132
103 | 0 | 372243.9701 | 372243.9701 | 107656.8132
104 | 0 | 372243.9701 | 372243.9701 | 107656.8132
105 | 0 | 372243.9701 | 372243.9701 | 107656.8132
106 | 0 | 383411.2892 | 383411.2892 | 118824.1323
107 | 0 | 383411.2892 | 383411.2892 | 118824.1323
108 | 0 | 383411.2892 | 383411.2892 | 118824.1323
109 | 0 | 383411.2892 | 383411.2892 | 118824.1323
110 | 0 | 383411.2892 | 383411.2892 | 118824.1323
111 | 0 | 383411.2892 | 383411.2892 | 118824.1323
112 | 0 | 383411.2892 | 383411.2892 | 118824.1323
113 | 0 | 383411.2892 | 81151833.2682 | 42451473.4974

## Annual
Year | Cost | NOI / sales | Levered cash
1 | 6936547.8101 | 0 | -6936547.8101
2 | 38591165.0983 | 0 | -21542791.9281
3 | 25670636.4371 | -230412.1448 | 0
4 | 0 | -367739.1913 | 0
5 | 0 | 3515269.3438 | -8457235.5711
6 | 0 | 4108310.9316 | 933265.0491
7 | 0 | 4231560.2595 | 1056514.377
8 | 0 | 4358507.0673 | 1183461.1848
9 | 0 | 4489262.2793 | 1314216.3968
10 | 0 | 2300467.7352 | 43045594.159

## Hold
Year | NOI | Debt service | Cash flow | DSCR | Cash on cash | Sale price | Net proceeds | Equity IRR | Property IRR
1 | 4368347 | 3175045.8624 | 1193301.1376 | 1.3758 | 3.085% | 78250000 | 36163418.9549 | -3.411% | 2.304%
2 | 4499397.41 | 3175045.8624 | 1324351.5476 | 1.4171 | 3.424% | 80598000 | 38934796.8343 | 3.581% | 5.446%
3 | 4634379.3323 | 3175045.8624 | 1459333.4699 | 1.4596 | 3.773% | 83016000 | 41807323.2972 | 5.959% | 6.513%
4 | 4773410.7123 | 3175045.8624 | 1598364.8499 | 1.5034 | 4.133% | 85506000 | 44785210.7888 | 7.125% | 7.05%
5 | 4916613.0336 | 3175045.8624 | 1741567.1712 | 1.5485 | 4.503% | 88072000 | 47874787.6293 | 7.801% | 7.373%

## Sensitivity
Input | Low case | Result | High case | Result
Rents (or sale prices) | −10% | -2.124% | +10% | 8.7%
Hard and site cost | −10% | 6.891% | +10% | 0.4721%
Exit cap rate | +0.50% | 1.47% | −0.50% | 5.611%
Stabilized vacancy | +2 pts | 2.323% | −2 pts | 4.667%
Construction loan rate | +1.00% | 3.087% | −1.00% | 3.919%
Construction period | +3 months | 3.179% | −3 months | 3.847%
Land price | +15% | 3.274% | −15% | 3.74%
levIrr grid | −10% rent
| −10% rent | −5% rent | 0% rent | +5% rent | +10% rent
−10% cost | 1.082% | 4.049% | 6.891% | 9.625% | 12.26%
−5% cost | -0.566% | 2.354% | 5.149% | 7.837% | 10.43%
0% cost | -2.124% | 0.7536% | 3.505% | 6.149% | 8.7%
+5% cost | -3.602% | -0.7626% | 1.949% | 4.552% | 7.062%
+10% cost | -5.007% | -2.202% | 0.4721% | 3.037% | 5.509%
levIrr grid | −1.00% rates
| −1.00% rates | −0.50% rates | 0.00% rates | +0.50% rates | +1.00% rates
−0.50% exit cap | 6.635% | 6.093% | 5.611% | 5.178% | 4.785%
−0.25% exit cap | 5.542% | 5.015% | 4.547% | 4.128% | 3.749%
0.00% exit cap | 4.466% | 3.956% | 3.505% | 3.102% | 2.738%
+0.25% exit cap | 3.402% | 2.913% | 2.48% | 2.095% | 1.747%
+0.50% exit cap | 2.348% | 1.881% | 1.47% | 1.104% | 0.7752%

## Scenarios
Scenario | Total cost | NOI | Yield on cost | Levered IRR | Profit
Base case | 79227647.635 | 3853211.0225 | 4.863% | 3.505% | 10596475.8575
Rates +1% | 80432125.9454 | 3853211.0225 | 4.791% | 2.738% | 8789960.0172
More one-bedrooms | 79236638.0643 | 3551169.3185 | 4.482% | 1.133% | 3361368.3646
Costs +10% | 85976615.5217 | 3747043.7611 | 4.358% | 0.3847% | 1227520.7476

## Risks
Level | Category | Risk | Why | What settles it
high | Returns | Thin development spread | Yield on cost 4.86% against a 5.5% market cap rate: -0.64% of spread (1.0–1.5% is the usual minimum to build rather than buy). | Firm up rents and costs; a lower land basis or a denser program.
high | Returns | Levered IRR below a typical 12–15% development hurdle | Levered IRR 3.51% over 9.4 years. | Test the scenarios: financing, unit mix and costs.
high | Returns | Returns turn negative on a common miss | Rents (or sale prices) −10% takes the levered IRR to -2.12%. | Price the biggest driver first (rents (or sale prices)).
medium | Returns | Negative NPV at the discount rate | Levered NPV $-11,255,356 at 10%. | Revisit the hurdle or the deal.
medium | Site | Parcel lines are not a survey | Areas come from appraisal-district or provider outlines. | A boundary survey (or enter its metes and bounds at intake).
medium | Site | Detention sized by rule of thumb | Detention 8.79 ac-ft from a typical release rate, not the jurisdiction’s criteria. | A drainage study by a civil engineer.
medium | Cost | Costs are parametric, not bids | Building lines come from one Waller County project workbook (medium-low confidence) and platform rates (low confidence); none is a contractor price. | A GC budget or a cost consultant’s estimate.
low | Site | Flood zone not checked | The site’s FEMA zone wasn’t looked up for this study. | Open the project’s Overview to look up the site.
low | Market | No sale or lease comps | Cap rates and rents are platform assumptions; Texas does not disclose sale prices. | Broker opinion of value or a licensed comps provider.